## 1. Meeting Actions
Product × Commercial — Meeting Actions Tracker
HOW TO USE: One row per action. Update Status/Next Step before each monthly meeting. Grey italic row below is an example — overwrite or delete it. Owner/Status/Priority are dropdowns.
ID | Action / Topic | Raised in Meeting | Owner | Priority | Status | Next Step | Target / Due | Notes
EX | EXAMPLE — Confirm Q3 Plinko release date with Product | Sep 2026 (Session 2) | Product | High | In Progress | Product to confirm target quarter | Next meeting | Example row — delete before use
A1 | Product roadmap accessible via Global Product SharePoint folder (status + target dates) | Session 2 | Kelly | High | In Progress | Jason to commit Product team to keep it updated | Before Sess. 3 | Kelly has folder access; Jason committing Product team to maintain content
A2 | Establish action/roadmap follow-up so each meeting reviews prior items | Session 2 | Kelly | High | In Progress | Stand up this tracker + share with group | Before Sess. 3 | This workbook
A3 | Share product demos/visuals so Commercial can prepare (e.g. cricket roulette demo from Josh) | Session 2 | Product | Medium | Open | Product to circulate available demos | Ongoing | Josh has cricket roulette demo; Kelly to request
A4 | Astro → Betman integration plan | Session 2 | Product | High | Open | Product to confirm approach & rough timing | TBD | Jason flagged as a specific requirement
A5 | Third-party games — strategic review + business case (continue or not, outside Aviator) | Session 2 | Commercial | High | Open | Review Paul's earlier analysis; commercial to build case | TBD | Needs decision + possible dedicated resource
A6 | Mobile POS / retail opportunity — commercial validation before final decision | Session 2 | Retail team | Medium | Open | Retail (Dieg/Tony/Tom) to finalise business case w/ data | TBD | East Africa / Golden Race competitive pressure
A7 | Competitive product analysis (our products vs competitors) — agree owner & scope | Session 2 | TBD | Medium | Open | Assign an owner at Session 3 | Sess. 3 | Identified gap — no owner yet. TBD (not Kelly)
A8 | Insight-driven product performance view (narrative, not just Power BI) | Session 2 | TBD | Medium | Open | Assign an owner at Session 3; agree format | Sess. 3 | Identified gap; possible AI-assisted approach. TBD (not Kelly)
A9 | Link GTM / customer comms more closely to upcoming releases | Session 2 | Commercial | Medium | Open | Feed into Patrick's GTM board | Ongoing | Philip/Josh/Jade → Patrick's board
A10 | Share recent football / cinematic updates with team + marketing | Session 2 | Marketing | Medium | Open | Product to send footage; confirm in marketing assets | Before Sess. 3 | Sarah requested; Jason has video
A11 | Propose meeting structure / action-tracking to group for input | Session 2 | Kelly | High | In Progress | Share workbook + structure doc; sign-off from Feron & Jason | Before Sess. 3 | Kelly's deliverable; leads = Feron (commercial) & Jason (product)
A12 | Schedule next monthly session (proposed 18 Sep, 11:00–12:00) | Session 2 | Kelly | High | In Progress | Confirm availability, send invite | 18 Sep | Awaiting confirmations

## 2. Product Roadmap
Product Roadmap Updates (Product owns content — Commercial reference)
HOW TO USE: Product brings updates to each meeting. Stage = Concept / In Dev / Staging / Production. 'Status Change' notes movement since last meeting. Channel & Stage are dropdowns.
ID | Channel | Product / Feature | Description | Stage | Target Release | Commercial Angle | Status Change | Updated
EX | VSE | EXAMPLE — New race track pack | Additional dirt/turf tracks for Betmakers global launch | Concept | Q4 2026 | Variety for global distribution | New | Example
P1 | VSE | One-minute horse racing (sprint) | Shorter event envelope following Entain success; English-look sprint product | In Dev | ASAP | Match Entain need; roll across all online racing | Priority | Sep 2026
P2 | VSE | Sprint dog racing | Switch dog racing to shorter single-loop format | Concept | TBD | Consistency with sprint racing | New | Sep 2026
P3 | VSE | Faster football (1-min envelope) | 6-goal game completing within one minute | In Dev | TBD | 1-min game intervals online | In progress | Sep 2026
P4 | VSE | New race tracks (variety) | 6–8 tracks incl. more dirt for US/global | Concept | Post-Betmakers | Needed for Betmakers global deal | New | Sep 2026
P5 | VSE | Racing visuals refresh | Modernised preamble/results, more energetic horse animation | In Dev | With sprint | Refresh vs 2015-era look | In progress | Sep 2026
P6 | Instant | Italian 3-goal micro-betting football | Header/penalty/L-R foot/save micro events | In Dev | TBD | Italian operators keen | In progress | Sep 2026
P7 | Instant | iGoal / Bet Power | Sustained-revenue instant football; strong margin | Production | Live | Retains revenue vs slots | Stable | Sep 2026
P8 | Instant | 'Hop' — new math game | Original simple math-based instant game | Concept | After racing | New original IP | New | Sep 2026
P9 | Instant | Cricket roulette | Demo available (Josh) — target Stake | Concept | TBD | Steven pushing to Stake | Demo ready | Sep 2026
P10 | Betman | Mobile / retail wallet | Voucher-based play across terminals & mobile in-venue | Staging | Post v6 | Transformative for African retail | New release | Sep 2026
P11 | Betman | Vision X + Net4Media (racing) | Horse then dog racing on Net4Media to cut bandwidth | Concept | TBD | Bandwidth-light shop content | Next up | Sep 2026
P12 | Betman | Football cinematic close-ups | New close-up/replay sequences; multilingual soccer | Production | Live | Marketing asset for customers | Recently shipped | Sep 2026

## 3. Commercial Requests
Commercial / Customer Requests (Commercial brings to each meeting)
HOW TO USE: Commercial logs what customers/markets are asking for. Link to a Product Roadmap ID where relevant. This is the 'two-way' input the meeting is built around.
ID | Date Raised | Customer / Market | Tier | Request / Feedback | Product Area | Linked Roadmap ID | Status | Owner | Notes
EX | 01 Sep 26 | Betway (SA) | Tier 1 | EXAMPLE — Interested in Plinko-style game | Instant | — | Open | Commercial | Example row — delete before use
C1 | Sep 26 | Third-party game clients | — | Want newest Astro / ESA / other third-party games distributed | Betman | P-Astro | Open | Commercial | Blocked on Betman integration
C2 | Sep 26 | Ethiopia market | — | Market entry — third-party (Galaxis/Smartsoft/Split the Pot) interest | Cross | — | Parked | Commercial | Prove payment first (Jason) before more games
C3 | Sep 26 | Italian operators | Tier 1 | Keen on 3-goal micro-betting football | Instant | P6 | Open | Commercial | Salivating per Jason
C4 | Sep 26 | East Africa retail | — | Retail solution to counter Golden Race | Betman | — | Open | Retail team | Mobile POS business case

## 4. Decisions & Questions
Decisions & Open Questions
HOW TO USE: Log the big yes/no calls and unresolved questions so the 'stake in the ground' is recorded. Type = Decision or Question.
ID | Type | Item | Detail | Owner | Status | Decision / Answer | Date
EX | Decision | EXAMPLE — Continue third-party slots? | Whether to endure beyond proof-of-concept | Commercial | Open | Pending business case | Example
Q1 | Question | Do we continue third-party games (outside Aviator)? | Thin margins; needs dedicated resource + channel | Commercial | Open | Awaiting business case & commercial decision | Sep 26
Q2 | Question | Do we stay in East Africa retail? | Golden Race pressure; mobile POS viability | Retail team | Open | Needs data-backed argument | Sep 26
Q3 | Question | Who owns competitive analysis + product-performance narrative? | Two identified gaps with no owner (not Kelly) | TBD | Open | Session 3 agenda item: assign an owner | Sep 26
D1 | Decision | Move to one-minute racing events | Testing on Betman OK; move ahead | Product | Done | Proceeding — sprint format | Sep 26
D2 | Decision | Cancel full CG racing revamp | Poor results vs cost | Product | Done | Cancelled; refine current instead | Sep 26
D3 | Decision | Ethiopia: prove payment before more games | Sequence risk down | Commercial | Done | Go live w/ existing, 1 month, then expand | Sep 26