Product × Commercial Monthly Session

Meeting structure & operating rhythm  —  proposal for input

Purpose:  Bridge the gap between what Product is building on the roadmap and Commercial's ability to prepare customers, create awareness, and feed customer demand back into Product. A two-way conversation, held monthly.

Leads:  Feron (Commercial) and Jason (Product).  This structure is shared with them for sign-off before adoption.

Standing agenda

Each section is brought by its owner. The facilitator keeps time and captures actions — the facilitator does not own the content of Product or Commercial sections.

| Agenda Section | Led by | Time |
| --- | --- | --- |
| 1. Previous actions review (what moved since last meeting) | Facilitator | 10 min |
| 2. VSE roadmap & upcoming releases | Product | 10 min |
| 3. Instant Games roadmap | Product | 10 min |
| 4. Betman roadmap & features | Product | 10 min |
| 5. Commercial / customer feedback & requests | Commercial | 10 min |
| 6. Product performance & market insights | Commercial / Product | 5 min |
| 7. Competitive & product opportunities | Commercial | 5 min |
| 8. GTM / customer readiness for releases | Commercial / Marketing | 5 min |
| 9. New actions, owners & decisions (incl. assign owner for the two gaps) | Facilitator | 5 min |

How each product topic is handled

For every roadmap item we run the same loop, so meetings stop starting from scratch:

- What did we say last time?  (pull from the tracker)

- Where is it now?  (stage / target date / status change)

- What's coming next?

- What does Commercial need to do with it?  (GTM, customer comms, demos)

Roles

- Facilitator:  schedules the session, sets the agenda, maintains the tracker, captures decisions & actions, circulates the summary, and makes sure the right info flows between Product and Commercial. Does not own content.

- Jason (Product lead):  commits the Product team to keep the roadmap updated in the Global Product SharePoint folder; brings updates, demos and target dates.

- Feron (Commercial lead):  brings customer/market requests and competitive intel; owns GTM readiness.

- Owners TBD (not the facilitator):  competitive analysis and the product-performance narrative have no owner — assigning one is a Session 3 decision. The facilitator tracks that it gets assigned; it does not default to the facilitator.

Operating rhythm (between meetings)

- ~1 week before:  facilitator asks Product for roadmap updates / demos, and Commercial for customer feedback & requests.

- ~2 days before:  facilitator circulates the agenda and the outstanding-actions list.

- At the meeting:  review previous actions first, then work the agenda; capture new actions, owners and decisions live.

- After the meeting:  facilitator sends a short summary — discussed / decided / actions + owners — and updates the tracker.

Supporting tools

- Action & roadmap tracker (this workbook):  Meeting Actions · Product Roadmap · Commercial Requests · Decisions & Open Questions.

- Global Product SharePoint folder:  single home for the product roadmap with status and target dates. Access is in place; Jason to commit Product team to keep it updated.

- Patrick's GTM board:  where release-readiness feeds the commercial team.

Cadence: monthly.   Next session proposed: Thursday 18 September, 11:00–12:00 (awaiting confirmation).